## Sheet1
Category	Task	Expected	Notes
Data	Test data & incorrect data to be deleted or edited	-	Admins (MG & AL) can do this		Green – done, needs testing
Db / User interface	Export of data to other dbs	WAITING	Shouldn't be a problem but a task for later		Italic – in progress
Documentation	Write formal user manual with MG	WAITING	Will look at this after other tasks		Gray – deferred
Documentation	Screencasts, videos	WAITING	Will do after other tasks. How/where to host videos
Data	Rename A(H1N1)pdm to A (H1N1) pdm09	Week 1	Admins can do this, I'll take care of it
Security & access	Users can see country data other than their own	Week 1	Investigated. Listing obeys security but tools don't
User interface	Garble in login page	Week 1
User interface	Rename susp reports to susp entries	Week 1	Hairy – we already have an entity called a susceptibility report
User interface	Rename collected specimen to specimen collected date	Week 1
User interface	Rename date of illness to date or onset	Week 1	Add help text. Get checked by others.
User interface	Rename susp entries to phenotypic analysis	Week 1
User interface	Rename measure to IC50	Week 1
User interface	Rename susp sequences to genotypic analysis	Week 1
User interface	Rename seq mutation to resistance associated mutation	Week 1
Db / User interface	Expand & rename antiviral exposure	Week 1-2	Will require db model change
User interface	Rename disease progression	Week 1-2
User interface	Rename resistance to drug	Week 1-2
Tools	Incorporate subtypes into uploads	Week 2	Subtype must match exactly what is in system
User interface	Add fields to assay for pyrosequencing etc	Week 2	Check db implications
User interface	user can only upload to own country	Week 2	Should be fixed by permissions fix, check
User interface	Validate date so it falls within season	Week 2
User interface	Validation of IC50 value	Week 2-3	Must be 0.0 or greater, check wider validation
Db / User interface	Add field for assay	Week 3	Check implications of this
Db / User interface	Make a download or files section for users	Week 3	Will require a bit of db work. Should roll other sections into here. Put on main toolbar.
User interface	Make SNP book more logical, better size & validate	Week 3	% reports are a bit sticky, have to validate & store correctly
Tools	Graphing tool	Week 3-4	Roll out graphing tool & others
Tools	Incorporate threshold into season uploads	Week 4
Tools	Incorporate patient data into uploads	Week 4-5	This was problematic when AA & I looked at it, must think carefully about format
Security & access	Add user level that can add, read but not edit or delete	WONTFIX	Requested by Brazil. Low priority & have no time for this.